## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-03-a TheRestfulGods (Team 7)
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As a buyer I want to create an account for the e-store so that I can shop on the e-store. | Given I want to create an account when I go to the sign up page then I expect to see a place put in information to create an account.
Given my entered username is already taken when I try to create my account then I get a message telling me to pick a new username.
Given my entered username is not taken when I try to create my account then my account information is saved and I am logged into my account.
Given I am on the user sign up page when I click the button to go to the login page then I get taken to the login page.
As a buyer I want to access a login page so that I can log into my account. | **Given** I want to access my account **when** I go to the login page **then** I expect to see a place put in my credentials and access my account.
Given I am on the user login page page when I click the button to go to the sign up page then I get taken to the sign up page.
Given I am on the user login page page when enter my correct username and password then I am logged into my account.
Given I am on the user login page page when enter an incorrect username and password then I am given a message explaining that my information was not correct.
As a admin I want to be able to see and add to my inventory from the main page so that I can run my e-store. | Given I need to change some of the e-store information when I log in as admin then I expect to see unique options to change executes changes to the store.
Given I am logged in as an admin when I view my main page then I can search products, browse, select products, and create new products.
As a admin I want to view the details of a single product and be able to modify or delete it so that I can manage my e-store. | Given I am logged in as an admin when I go to a product's page then I should be able to see all of its information.
Given I am logged in as an admin when I go to a product's page then I should be able to modify all of its information.
Given I am logged in as an admin when I go to a product's page then I should be able to delete the product.
Given I am logged in as an admin when I delete a product then the product should be removed from the inventory store and I should be brought back to the main page.
Given I am on a product's page when I click the button for the main page then I should be brought back to the main page.
As a user (buyer or admin) I want to search for products in a search bar so that I can find the type of products I'm looking for. | Given I want to find an item when I access the search option then I expect to be able to see and browse through all products that meet the search specification.
Given there are products in the inventory when I put text in the search bar then I should see every product that has that text in any field (other than price), and not see any that don't.
Given I delete the specified search string when products associated with it are displayed on the webpage then the system should re-update the webpage with all products, as originally displayed.
As a user (buyer or admin) I want to browse available products so that I can see the available options to purchase. | Given I am logged in when I view the browsing page then I see all available products.
Given I am logged in when I click on a product then I am brought to its product page.